## Risk Approach
Consequence/Likelihood Table
Consider the consequences and likelihood for each of the identified hazards / risk and use the table to obtain the risk level. The following table can be used to identify the level of risk and help to prioritise any control measures. This may be used for determining all levels of risk and not OH&S type risks only. Define the risk – define the likelihood and potential consequence then apply the controls and continue to monitor the risk.
Consequences
|  |  | 1 – Insignificant | 2 – Minor | 3 – Moderate | 4 – Major | 5 – Severe
Likelihood | 5 | Almost certain to occur in most circumstances | Medium (M) | High (H) | Extreme (X) | Extreme (X) | Extreme (X)
| 4 | Likely to occur frequently | Medium (M) | High (H) | High (H) | Extreme (X) | Extreme (X)
| 3 | Possible and likely to occur at some time | Low (L) | Medium (M) | High (H) | High (H) | Extreme (X)
| 2 | Unlikely to occur but could happen | Low (L) | Low (L) | Medium (M) | High (H) | High (H)
| 1 | May occur but only in rare circumstances | Low (L) | Low (L) | Medium (M) | Medium (M) | Medium (M)
How to prioritise the Risk Rating
Once the level of risk has been determined the following table may be of use in determining when to act to institute the control measures.
Extreme (X) | Act immediately to mitigate the risk. Either eliminate, substitute or implement control measures. |  |  | Remove the hazard at the source. An identified extreme risk does not allow scope for the use of administrative controls or PPE, even in the short term.
High (H) | Act immediately to mitigate the risk. Eliminate, substitute or implement control measures. If these controls are not immediately accessible, set a timeframe for their implementation and establish interim risk reduction strategies for the period of the set timeframe. |  |  | An achievable timeframe must be established to ensure that elimination, substitution or controls are implemented. NOTE: Risk (and not cost) must be the primary consideration in determining the timeframe. A timeframe of greater than 6 months would generally not be acceptable for any hazard identified as high risk. Interim measures until permanent solutions can be implemented: • Develop administrative controls to limit the use or access. • Provide supervision and specific training related to the issue of concern. (See Administrative Controls below)
Medium (M) | Take reasonable steps to mitigate the risk. Until elimination, substitution or engineering controls can be implemented, institute administrative or personal protective equipment controls. These “lower level” controls must not be considered permanent solutions. The time for which they are established must be based on risk. At the end of the time, if the risk has not been addressed by elimination, substitution or other controls a further risk assessment can be undertaken.
Low (L) | Take reasonable steps to mitigate and monitor the risk. Institute permanent controls in the long term. Permanent controls may be administrative in nature if the hazard has low frequency, rare likelihood and insignificant consequence.
Consequence Matrix
Rating | Level | Injury | Financial Loss | Operational Efficiency | Compliance | Information & Evidence | Reputation | The project, as it has been defined by the Project Team, is unviable. | Permanent disruption to capability, Mission critical financial loss, ruinous impact on community, widespread and sustained adverse media coverage, criminal guilt/ death, non adherence to governing State Legislation
Catastrophic | 5 | Death | >6% | Delay > 1 month Non-achievement of major business activity | Non-compliance resulting in criminal charges or loss of accreditation | Loss, unauthorised release or access to information resulting in the cancellation of an operations(s) and / or total compromise of system | Substantiated Public embarrassment Very High Impact High media profile Third Party Action | Major event or string of events that endanger the implementation of the overall project as defined by the Project Team | Ongoing disruption to capability, major financial loss, major impact on standing, Occupational threat of ongoing injury, major state legislation infringements.
Major | 4 | Permanent disability or disease | 2% to 6% | Delay (1 week - 1 month) with potential for non achievement of major objectives | Non compliance resulting in penalties | Loss, unauthorised release of access to information resulting in substantial compromise of operations and /or systems | Substantiated Public embarrassment High Impact High media profile Third Party Action | Event that has a moderate impact on some of the following items: vision, planning, program, scope, costs. | Modest impact on capability and lost time, moderate financial loss, some media coverage and impact on standing moderate injuries, minor state legislation infringements
Moderate | 3 | Medical Treatment | 0.15% to 2% | Delay (1 day - 1 week) in achievement of business objectives | Compliance or probity infringements | Loss, unauthorised release of access to information resulting in significant compromise of operations and /or systems | Substantiated Public embarrassment Moderate Impact Moderate media profile Third Party Action | Minor implication on the vision or the planning, or the program or the scope or the economic balance | Minor disruption to capability, minor financial loss, minor impact on community standing, low grade injuries
Minor | 2 | First Aid Treatment | 0.025% - 0.15% | Delay (2 hours - 1 day) in performance limiting full achievement of business objectives | Some minor, non compliance issues | Loss, unauthorised release or access to information resulting in minor compromise of operations and /or systems | Substantiated Public embarrassment Low Impact Low media profile Third Party Action | No/insignificant implication on the vision, planning, program, scope and economic balance of the project | No disruption to capability, low financial loss, no impact on community standing
Insignificant | 1 | No injuries or health affects | Up to 0.025% | Delay (up to 2 hours) in performance all business objectives still achieved | Guidance required for compliance | Loss, unauthorised release or access to information resulting in an insignificant impact on operations and/or systems | Substantiated Public embarrassment Low Impact Low or No media profile
Likelihood Matrix
Descriptor | Level | Common meaning | Example
Almost Certain | 5 | Greater than 90% chance of occurring. | Is expected to occur in most circumstances
Likely | 4 | 51% to 90% chance of occurring | Will probably occur in most circumstances
Possible | 3 | 30% to 50% chance of occurring. | Might occur at some time
Unlikely | 2 | Between 5% and 30% chance of occurring | Could occur at some time
Rare | 1 | Less than 5% chance of occurring | May Occur at some time
Hierarchy of Controls
Elimination | Eliminate the hazard, threat or issue
Substitution | Provide an alternative that is capable of performing the same task and is safer / appropriate to use.
Engineering Controls | Provide or construct a physical barrier or guard or other controls.
Administrative Controls | Develop policies, procedures practices and guidelines, in consultation with to mitigate the risk. Provide training, instruction and supervision about the hazard.
Personal Protective Equipment | Personal equipment designed to protect the individual from the hazard.
Risk Strategy
Avoid Risk | Change plans to circumvent the problem
Control/Mitigate Risk | Reduces impact or likelihood (or both) through intermediate steps
Accept Risk | Take the chance of negative impact (or auto-insurance), eventually budget the cost (e.g. via a contingency budget line);
Transfer Risk | Outsource risk (or a portion of the risk - share risk) to third party/ies that can manage the outcome.
Glossary of Terms
Consequence
The outcome or impact of an event that can be expressed in a quantitative or qualitative way. There can be more than one consequence from one event and consequences can range from positive to negative. Consequences are usually considered in relation to the achievement of objectives.
Control
An existing process, policy, device, practice or other action that acts to minimise negative risk or enhance positive opportunities and includes a process designed to provide reasonable assurance regarding the achievement of objectives.
Event
The occurrence or change of a particular set of circumstances. The event can be certain or uncertain and can be a single occurrence or a series of occurrences.
Likelihood
Refers to the chance of something happening, whether defined, measured or estimated objectively or subjectively, or in terms of general descriptors (i.e. rare, unlikely, likely, almost certain), frequencies or probabilities. As ‘probability’ is often interpreted more formally in English as a mathematical term, ‘likelihood’ is used throughout this policy.
Level of Risk
The magnitude of risk or a combination of risks, expressed in terms of consequences and their likelihood.
Monitor
To check, supervise, observe critically or measure the progress of an activity, action or system on a regular basis in order to identify change from the performance level required or expected
Organisation
Group of people and facilities with an arrangement of responsibilities, authorities and relationships. Can include company, corporation, firm, enterprise, institution, association, or parts or combination thereof.
Residual risk
The risk remaining after implementation of controls and risk treatments
Risk
The effect of uncertainty on objectives. An effect is a deviation from the expected, positive and/or negative. Objectives can have different aspects and can apply at different levels. A risk is often characterised by reference to potential events and consequences, or a combination of these. Risk is often expressed in terms of a combination of the consequences of an event and the associated likelihood of occurrence. Uncertainty is the state of deficiency of information related to, understanding or knowledge of an event, its consequences or likelihood.
Risk analysis
A systematic process used to understand the nature of and to deduce the level of risk that provides the basis for risk evaluation and decisions about risk treatments.
Risk assessment
The overall process of risk identification risk analysis and risk evaluation
Risk avoidance
A decision not to become involved in, or to withdraw from, a risk situation.
Risk criteria
The terms of reference by which the significance of risk is assessed. Risk criteria can include associated cost and benefits, legal and statutory requirements, socioeconomic and environmental aspects, the concerns of stakeholders’ priorities and other inputs to the assessment.
Risk evaluation
The process of comparing the level of risk against risk Criteria. Risk evaluation assists in decisions about risk treatment.
Risk identification
The process of finding, recognising and describing risks.
Risk management
The coordinated activities to direct and control an organisation with regard to risk.
Risk management plan
A scheme within the risk management framework specifying the approach, the management components and resources to be applied to the management of risk.
Risk management policy
The statement of the overall intentions and direction of an organisation related to risk management.
Risk management process
The systematic application of management policies, procedures and practices to the tasks of communicating, establishing the context, identifying, analysing, evaluating, treating, monitoring and reviewing risk.
Risk management framework
The set of elements of an organisations’ management system concerned with managing risk. Management system elements can include strategic planning, decision making, and other processes and practices for dealing with risk. The culture of an organisation is reflected in its risk management system.
Risk owner
A person or entity with the accountability and authority to manage risk.
Risk reduction
Actions taken to lessen the likelihood, negative consequences or both, associated with a risk
Risk retention
The acceptance of the burden of loss, or benefit of gain, from a particular risk. Risk retention includes the acceptance of risks that have not been identified. The level of risk retained may depend on risk criteria.
Risk sharing
The sharing with another party the burden of loss, or benefit of gain from a particular risk. Legal or statutory requirements can limit, prohibit or mandate the sharing of some risks. Risk sharing can be carried out through insurance or other agreements. Risk sharing can create new risks or modify an existing risk.
Risk treatment
The process of selection and implementation of measures to modify risk. The term ‘risk treatment’ is sometimes used for the measures themselves. Risk treatment measures can include avoiding, modifying, sharing or retaining risk.
Stakeholders
The people and organisations who may affect, be affected by, or perceive themselves to be affected by a decision, activity or risk. The term ‘stakeholder’ may also include ‘interested parties’ as defined in AS/NZS ISO 14050 and AS/NZS ISO 14004.

## Risk Register
| Category | Risk Statement | Risk Area | Consequence | Likelihood | Inherent Risk Rating | Possible Control/Treatment Options | Consequence | Likelihood | Residual risk rating | By when? | How will it be monitored | Further Action | Legislation | Standards/ Codes/ guidance
1.1(a) | Chemicals | · Chemical exposure - acute or chronic: - inhalation - absorption - ingestion - injection · Fire or Fire and/or explosion through incorrect storage, handling, labelling or mixing of chemicals · Time sensitive chemicals that can become unstable during storage · Production of hazardous wastes · Environmental contamination due to accidental leakage, spills, emissions: - air - water - soil/ground | OHS | 3 | 2 | 6 | · MSDS register · Chemical Risk Assessments · Purpose built storage areas for cylinders and compressed gases · Restricted access to authorised personnel · Correct labelling, storage and segregation · Scheduled workplace assessments that include chemical assessment · Time sensitive chemicals dated · Emergency procedures for accidental release/spillage · Health monitoring (when needed) · Exposure monitoring · Personal protective equipment (PPE) · Hazardous waste removal · Spill kit · First Aid | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996: Part 5 - Hazardous substances · Dangerous Goods Safety Act 2004 · Dangerous Goods Safety (General) Regulations 2007 · Dangerous Goods Safety (Storage and Handling of Non-explosives) Regulations 2007 · Poisons Act 1964 · Poisons Regulations 1965 · Excise Act 1901 (Commonwealth) · Excise Regulations 1925 (Commonwealth) · Water Corporation Act 1995 · Water Supply Sewerage and Drainage Act 1912 · Health (Treatment of Sewage and Disposal of Effluent and Liquid | STANDARDS: · AS/NZS 2229 Fuel Dispensing Equipment for Explosive Atmospheres · AS 1692 Steel Tanks for Flammable and Combustible Liquids · AS/NZS 1020 The Control of Undesirable Static Electricity · AS 1216 Class Labels for Dangerous Goods · AS 1940 The Storage and Handling of Flammable and Combustible Liquids · AS 2567 Laminar Flow Cytotoxic Drug Safety Cabinets · AS 2243 (series) Safety in Laboratories Part 2: 2006 - Chemical aspects Part10: 2004 - Storage of chemicals · AS/NZS 1596 The Storage and Handling of LP Gas · AS 1345 Identification of the Contents of Pipes, Conduits and Ducts · AS 2030 (series) The Verification, Filling, Inspection, Testing and Maintenance of Cylinders for Storage and Transport of Compresses gases · AS 1894 The Storage and Handling of Non-Flammable Cryogenic and Refrigerated Liquids · AS 4757 Handling and Destruction of Drugs · Standard for the Uniform Scheduling of Drugs and Poisons (Commonwealth) · National Standard Storage and Handling of Workplace Dangerous Goods [NOHSC:1015 (2001)] CODES OF PRACTICE: · Australian Dangerous Goods Transport Code Edition 6 & 7 · National Code of Practice for the Preparation of Material Safety Data Sheets [NOHSC:2011 (2003)] · National Model Regulation for the Control of Workplace Hazardous Substances [NOHSC:1005(1994)] · National Code of Practice for the Control of Workplace Hazardous Substances [NOHSC:2007(1994)] · Code of Practice for the Control of Scheduled Carcinogenic Substances [NOHSC:2014 (1995)] · National Code of Practice for the Labelling of Workplace Substances [NOHSC:2012 (1994)] · National Code of Practice for the Storage and Handling of Workplace Dangerous Goods [NOHSC:2017 (2001 GUIDANCE'S: · National Guidance Note - Assessing Risks of Hazardous Substances · National Guidance Note - Exposure Standards · Controlling Isocyanate Hazards at Work · Guidance Note for the Assessment of Health Risks Arising from the Use of Hazardous Substances in the Workplace [NOHSC:1317(1994)] · Approved Criteria for Classifying Hazardous Substances {NOHSC:1008 (2004)] · National Model Regulation for the Control of Scheduled Carcinogenic Substances [NOHSC:1011 (1995)] · National Code Storage and Handling of Workplace Dangerous Goods [NOHSC:1017 (2001)] · Hazardous Substances Information System (HSIS) web site (Commonwealth) · Adopted National Exposure Standards for Atmospheric Contaminants in the Occupational Environment [NOHSC:1011 (1995)] · Guidance Note on Interpretation of Exposure Standards for Atmospheric Contaminants in the Occupational Environment [NOHSC:3008(1995)] · Guidelines for Health Surveillance NOHSC:7039 (1995)]
1.2(a) | Infectious Diseases | · First aid activities | OHS | 3 | 2 | 6 | · Standard precautions of personal care · Additional precautions (for suspected confirmed infectious disease) · Human immunisation · Personal protective equipment · Health monitoring (when requireed) · First aid training | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 · Health Act 1911 (WA) | STANDARDS: CODES OF PRACTICE: · National Code of Practice - Hepatitis and HIV · National Code of practice for the Control of Work Related Exposure to Hepatitis and HIV (Blood-Borne) Viruses [NOHSC:2010 (2003)] GUIDANCE'S: · Australian Immunization Handbook (NHMRC) (Commonwealth) · Guidelines for Health Surveillance NOHSC:7039 (1995)] · Guidance Note - Reducing the Risk of Infectious Diseases in Childcare Workplaces – [WorkSafe WA] · Australian Government Department of Health and Aging Infection Control Guidelines 2004 · Australian Quarantine Inspection Service Department of Environment and Conservation
1.3 | Electrical | · Use of faulty equipment/appliances · Use of uncertified electrical equipment/appliances · Incorrect and/or faulty electrical installation · Substations and switchboards | OHS | 3 | 2 | 6 | · Pre-purchase safety considerations · Visual inspections for damage · Scheduled testing and tagging of portable electrical equipment · Tag out and remove from service damaged or faulty equipment · Qualified and competent electrical workers for design, manufacture and testing · Electrical installation by licensed electricians · Use of RCDs · RCD testing program · Signage · Workplace Inspections | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996: Part 4 - Plant · Electricity Act 1945 · Electricity (Licensing) Regulations 1991 · Electricity Regulations 1947 | STANDARDS: · AS 2243 (series) Safety in Laboratories Part 7: 1991 - Electrical aspects · AS/NZS 3000 Wiring Rules · AS/NZS 3000 Wiring Rules Appendix A Referenced Documents · AS/NZS 3105 Approval and Test Specification – Electrical and Portable Outlet Devices · AS/NZS 3199 Approval and Test Specification – Cord Extension Sets · AS/NZS 3760 In service Safety Inspection and Testing of Electrical Equipment · AS 3112 Approval and Test Specification – Plug and Socket Outlets · AS/NZS 1660 (series) Test Methods for Electric Cables, Cords and Conductors CODES OF PRACTICE: GUIDANCE'S: · Isolation of Plant (also cited under Plant and Equipment) · Guidance to testing & tagging portable electrical equipment
1.4(a) | Plant and Equipment | · Injury / Health impacts · Lack of operator competency / training · Unassessed plant and equipment · Lack of/inappropriate guarding · Unrestricted access · Poorly managed or maintained plant · Adverse impact on the environment: - waste generation from plant - decommissioning and removal of plant · Refer to “Electrical” · Refer to “Ionising Radiation” · Refer to “Non-Ionising Radiatio” | OHS | 4 | 2 | 8 | · Plant and Asset Registers · Pre purchase safety considerations · Plant Hazard and Risk Assessments · Guarding and engineering controls · Emergency stops · Training and supervision · Restricted access · Scheduled maintenance · Standard Operating Procedures · Tag Out Procedures · Personal protective equipment · Waste removal · Removal of decommissioned plant · Scheduled Inspections · First Aid · Licenses and Registration | 4 | 1 | 4 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 | STANDARDS: · AS 1893 Code of Practice for the Guarding and Safe Use of Metal and Paper Cutting Guillotines · National Standard for Plant [NOHSC:1010(1994)] CODES OF PRACTICE: · Safeguarding of Machinery and Plant GUIDANCE'S: Isolation of Plant [WorkSafe WA] (also cited under Electrical) · Plant Design [WorkSafe WA] (also cited under Workplace Design and Construction) · Plant in the Workplace [WorkSafe WA] (also cited under Workplace Design and Construction) · Powered Mobile Plant
1.4(b) | Noise | · Hearing impairment · Noise in excess of the exposure standards · Distracting noise · Noise impact on surrounding community | OHS | 3 | 2 | 6 | · Pre-purchasing checklist · Noise Risk Assessments (when required) · PPE - hearing protection · Signage · Restricted access | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 | STANDARDS: · AS 1055 (series) Acoustics – Description and Measurement of Environmental Noise · AS 1269 (series) Occupational Noise Management · AS 2822 Acoustics – Methods Of Assessing And Producing Speech Privacy And Speech Intelligibility · AS 2107 Acoustics – Recommended Design Sound Levels and Reverberation Times for Building Interiors CODES OF PRACTICE: · Managing Noise at Workplaces · Control of Noise in the Music Entertainment Industry · National Code of Practice for Noise Management and Protection of hearing at Work (NOHSC:2009 [2004]) GUIDANCE'S: · HB Occupational Personal Protection · Managing Noise at Work (Commonwealth)
1.4(c) | Traffic, Driving and Parking | · Injury and/or property damage · Speed · Unauthorised and/or unsafe parking | OHS | 3 | 2 | 6 | · Traffic management: - Controlled access into parking areas - Designated parking spaces - Walkways and pathways · Security Services | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 · Road Traffic Act 1974 · Road Safety Council Act 2002 · Road Traffic Administration Act 2008 · Road Traffic (Authorisation to Drive) Act 2008 | STANDARDS: · AS/NZS 4602 - 1999 High Visibility Safety Garments CODES OF PRACTICE: GUIDANCE'S: · Safe Movement of Vehicles at Workplaces [WorkSafe WA] · Safe Movement of Vehicles [WorkSafe WA]
1.4(d) | Firearms, Regulated and Prescribed Weapons | · Personal injury · Theft and misuse | OHS | 5 | 3 | 15 | · Licensed and trained personnel with access to firearms · Secure firearm storage · Register of firearms with Security · Personal Protective Equipment – hearing and eye protection · Routine cleaning and maintenance of firearms · Firearms training | 5 | 2 | 10 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 · Firearms Act 1973 | STANDARDS: CODES OF PRACTICE: · National Firearms Safety Code (Commonwealth) · WA Firearms Safety Handbook GUIDANCE'S:
1.4(e) | (e) Ionising Radiation (X-Ray Machines) | · Radioactive substances - External exposure - Internal contamination - Storage, transport, disposal · Irradiating apparatus - X-ray burns (skin, eyes) | OHS | 4 | 2 | 8 | · Radiological Council Registration of Radioactive Substances, Premise and Equipment; Licensing of Individuals · Pre-purchase checklist · Radiation Safety Officer · Risk Management (Risk Assessments, SOP’s, Method Statements) · Risk Management · Radiation Training · Radiation Audit program · Secured radiation storage · Radiation Protocols (risk assessments) · Personal monitoring (badges) · Contamination monitoring (wipe testing) · Central Radioactive Waste Store · Controlled Access · Signage · Supervision · PPE | 4 | 1 | 4 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health 1984 · Occupational Safety and Health Regulations 1996: Part 5 - Hazardous substances · Radiation Safety Act 1975 – 1999 · Radiation Safety (General ) Regulations 1983 – 2003 · Radiation Safety (Transport of Radioactive Substances) Regulations 2002 · Radiation Safety (Qualifications) Regulations 1980 - 2000 | STANDARDS: CODES OF PRACTICE: · National Code of Practice - Labelling of Workplace Substances · National Standard for Limiting Occupational Exposure to Ionizing Radiation [NOHSC:1013(1995)] · Code of Practice Exposure of Humans to Ionizing Radiation for Research Purposes (Commonwealth) · Code of Practice and Safety Guide for Radiation protection in Dentistry (Commonwealth) · Code of Practice for the Security of Radioactive Sources (Commonwealth) GUIDANCE'S: · Recommendations for Limiting Exposure to Ionizing radiation (1995) (Guidance Note [NOHSC:3022(1995)] · Maximum Exposure Levels to Radiofrequency Fields -- 3 kHz to 300 GHz, (Radiation Protection Series No. 3) · National Directory for Radiation Protection (Commonwealth) · Refer to “Plant” classification for plant Standards/Codes/Guidance
1.5 | Psychosocial | · Occupational stress · Workplace bullying and harassment · Violence (e.g. Occupational/Domestic) · Fatigue | OHS | 3 | 2 | 6 | · Mental Health Promotion - Health & wellbeing activities and workshops - Training and awareness · Case and Injury Management Support · Counselling support services (EAP) · Security Services · Training/ Induction (e.g. Bulling, Sexual Harassment) | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 | STANDARDS: CODES OF PRACTICE: · Violence, Aggression and Bullying at Work (SafeWork Australia) · Working Hours GUIDANCE'S: · Dealing with bullying at work (a guide for workers) (WorkSafe WA) · Dealing with workplace bullying - a worker's guide (SafeWork Australia) · Guide for preventing and responding to workplace bullying (SafeWork Australia) · Guide for managing the risk of fatigue at work (SafeWork Australia) · Fatigue management - a worker's guide (SafeWork Australia)
2.1 | Workplace Environment, Facilities and Administration | · Poor ergonomic and work station layout · Poor storage and office space · Poor environmental characteristics: - thermal discomfort - nuisance noise - inadequate lighting - Glare · Poorly maintained equipment · Office waste · Inadequate access to facilities including: - toilets - washing facilities - drinking water - dining facilities · Emergency access and egress | OHS | 3 | 3 | 9 | · Provision of facilities: - toilets - washing facilities - eating · Workplace design · Ergonomic assessments · Incident, Near Miss and Hazard reporting and follow-up · Workplace inspections · Office waste removal and recycling · Planned preventive maintenance | 3 | 2 | 6 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996: Part 3 - Workplace Safety Requirements | · STANDARDS: · AS 1680 (series) Interior Lighting · AS 3590 (series) Screen-Based Workstations · AS 2107 Noise in Offices · AS 2822 Acoustics – Methods Of Assessing And Producing Speech Privacy And Speech Intelligibility · AS 2107 Acoustics – Recommended Design Sound Levels and Reverberation Times For Building Interiors · AS/NZS 1668 (series) The Use Of Ventilation And Air Conditioning In Buildings · AS/NZS 4438 Height Adjustable Swivel Chairs · AS/NZS 4442 Office Desks · AS/NZS 4443 Office Panel Systems – Workstations · AS/NZS 2466 Guide to the Design of Microform Workstations CODES OF PRACTICE: · First aid, workplace amenities and personal protective clothing · National Code of Practice for the Prevention of Occupational Overuse Syndrome [NOHSC:2013 (1994)] GUIDANCE'S: · General Duty of Care in Western Australian Workplaces · Preparing for Emergency Evacuations at the Workplace · Ergonomic Principles And Checklists For The Selection Of Office Furniture And Equipment (Commonwealth) · Guidance Note for the Prevention of Occupational Overuse Syndrome in Keyboard Employment [NOHSC:3005 (1996)]
2.2 | Working Outdoors | · Exposure to adverse weather conditions: - uncontrolled environment - thermal (heat cold) - ultraviolet light exposure - rain - wind - lightning | OHS | 2 | 1 | 2 | · Risk Management (Risk Assessments, SOP’s, Method Statements) · Scheduled work at appropriate times, seasons and weather conditions · Standard operating procedures · PPE: - Wet weather gear - Long sleeved clothing - Sunhats - Sunglasses - Appropriate Footwear · Sunscreen · 30/30 lightning guidance · First Aid | 2 | 1 | 2 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 | STANDARDS: CODES OF PRACTICE: GUIDANCE'S: · Safe Movement of Vehicles at Workplaces · Radiation Protection Standard for Occupational Exposure to Ultraviolet Radiation (Commonwealth) · Guidance Note for the Protection of Workers from Ultraviolet Radiation in Sunlight [NOHSC:3012 (1991)]
2.3 | Workshops | · Injury and/or property damage · Unassessed plant and equipment · Poorly maintained equipment · Lack of/inappropriate guarding · Lack of operator competency / training · Hazards associated with the work undertaken. For example: - mechanical equipment - electrical equipment - industrial chemicals - fumes - wastes · Unrestricted access · Refer to specific hazard | OHS | 3 | 1 | 3 | · Specialised facilities, restricted access · Appropriate selection and maintenance of equipment, tools and chemicals · Risk Management (Risk Assessments, SOP’s, Method Statements) · Training, including induction · Standard operating procedures · Good housekeeping · Management of wastes · Audit/Inspections · First Aid · PPE | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 | STANDARDS: CODES OF PRACTICE: · First aid, workplace amenities and personal protective clothing · National Code of Practice - Labelling of Workplace Substances · Health and Safety in Welding – Tech Note 7 GUIDANCE'S: · Plant in the Workplace · Prevention of Carbon Monoxide Poisoning
2.4 | Confined Spaces | · Asphyxiation · Entrapment · Unrestricted access to confined spaces · Inadequate risk assessment of confined space · Inadequate identification of confined space · Poorly ventilated workplaces | OHS | 3 | 2 | 6 | · Confined space requirements · Confined space register · Confined space entry permit system · Confined space entry training · Confined space emergency procedures · Safety signage · Restricted access | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996: Part 3, Division 8 | STANDARDS: · AS/NZS 2865 Safe Working in a Confined Space CODES OF PRACTICE: GUIDANCE'S: · HB 213 Guidelines for Safe Working in a Confined Space
2.5 | Working at Heights Above 2 Metres | · Fall from height · Working close to an edge unprotected · Unsuitable working environment: - slippery roof - brittle roof - adverse weather conditions (wind and rain) · Unsecured equipment · Inappropriate use of access and/or fall arrest equipment · Faulty, poorly maintained or inappropriate use of: - Ladders - Scaffold - elevated work platform - harnesses and lanyards - anchor points | OHS | 4 | 3 | 12 | · Fall protection: - Handrails and barriers - Elevated work platforms - scaffolding - edge protection · Fall arrest and anchor point systems · Standard Operating Procedures · Height safety training (including recovery and emergency response) · Accessing heights under suitable weather conditions (e.g. not raining and little/no wind) · Restricted access and entry points · Barricading · Equipment testing · PPE | 4 | 2 | 8 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 | STANDARDS: · AS/NZS 1891 (series) Industrial Fall-Arrest Systems and Devices · AS/1657 Fixed Platforms, Walkways, Stairways and ladders – Design, Construction and Installation · AS/NZS 1892 (series) Portable Ladders CODES OF PRACTICE: · Prevention of Falls at Workplaces 2004 (WA) GUIDANCE'S:
3.1 | Manual Handling and Ergonomics | · Manual handling tasks/activities that include the following characteristics: - repetitive or sustained application of force - repetitive or sustained awkward posture - repetitive or sustained movement - application of high force - exposure to sustained vibration · handling of a person or an animal · handling of unstable or unbalanced loads or loads which are difficult to grasp or hold | OHS | 3 | 3 | 9 | · Manual handling risk management plans · Manual handling training · Workstation ergonomic assessments · Mechanical aids and lifting devices: - trolleys - pedestrian stackers and walkers - platform ladders - hoists · Pre purchase safety considerations · Provision of ergonomic equipment | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 | STANDARDS: · National Standard for Manual Tasks (Commonwealth) See also Section 20 Workplace, Environment and Facilities CODES OF PRACTICE: · Manual Handling · National Code of Practice – Occupational Overuse Syndrome · National Code of Practice for Prevention of Musculoskeletal Disorders from Performing Manual Handling tasks at Work (Commonwealth) GUIDANCE'S:
3.2 | Travel and Off-location Activities | · Domestic travel · Overseas travel · Remote locations · Driving and travel arrangements · Inadequate communication · Unexpected events/emergencies | OHS | 3 | 2 | 6 | · International Travel Risk Assessment and Plan (when required) · Medical and security risk analysis · Travel communications Plan · 4WD training · Emergency response procedures · First aid · Induction · PPE | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 | CODES OF PRACTICE: · Fatigue Management for Commercial Vehicle Drivers GUIDANCE'S: · Smartraveller web site (Commonwealth) · Medical and Security Travel Support Services Provider web site · National Guidelines for Working Alone or in a Remote Locality [Commonwealth Safety Management Forum] (also cited under After Hours Work) · Department of Foreign Affairs and Trade website [Commonwealth]
3.3 | Workplace Design and Construction | · Introduction hazards/risks at design · Hazards/Risks associated with construction works: - electrical - plant - fall from heights - chemicals - manual handling - noise – changing environment o unauthorised access · Slip, trips and falls · Hazardous materials removal | OHS | 3 | 2 | 6 | · Workplace design standard · Project Managers · Risk management approach · Restricted/authorised access: - temporary fencing - signage · Contractor and site induction · Refer to specific hazard classification for controls · Hazardous materials removal · Routine maintenance · Incident reporting and follow-up actions | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996: Part 3 - Workplace Safety | Refer to specific hazard classification for Standards / Code / Guidance STANDARDS: · AS 2982.1 Laboratory Design and Construction – General Requirements · AS 1345 Identification of the Contents of Pipes, Conduits and Ducts · AS/NZS 3017 Electrical Installations – Verification Guidelines · AS/NZS 3019 Electrical Installations – Periodic Guidelines · AS/NZS 1576 (series) Scaffolding · AS/1657 Fixed Platforms, Walkways, Stairways and ladders – Design, Construction And Installation · AS 2436 Guide to Noise Control on Construction, Maintenance and Demolition Sites CODES OF PRACTICE: · Safe Design of Buildings and Structures 2008 · National Code of Practice – Synthetic Mineral Fibres · Safe Design of Buildings and Structures · Building Code of Australia (Commonwealth) GUIDANCE'S: · Plant Design (also cited under Plant and Equipment) · Plant in the Workplace (also cited under Plant and Equipment) · Prevention of Carbon Monoxide Poisoning · National Standard for Construction Work [NOHSC:1016 (2005)]
3.4 | Hot Work | · Fire and/or explosion · Injury and/or property damage | OHS | 3 | 2 | 6 | · Contractor and workshop requirements · Hot work permit system · Risk Management (Risk Assessments, SOP’s, Method Statements) · Training and Induction · Fire alarm systems · Fire fighting equipment · Scheduled maintenance for hot work plant and fire detection and fighting equipment · Scheduled building evacuations and exercises · PPE · First Aid | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 | STANDARDS: · AS 1335 Hoses and Hose Assemblies for Welding, Cutting and Allied Processes · AS/NZS 1338.1 Filters for Eye Protectors - Filters For Protection Against Radiation Generated In Welding And Allied Operations · AS/NZS 1554 (series) Structural Steel Welding · AS 1674 (series) Safety In Welding And Allied Processes CODES OF PRACTICE: · Health and Safety in Welding – Tech Note 7 GUIDANCE'S: · Gas Welding Safety Flashback Arresters
3.5 | Smoking | · Passive smoking · Fires · Generation litter/butts | OHS | 3 | 1 | 3 | · No smoking on premises · No smoking in buildings or vehicles | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 · The Tobacco Products Control Act 2006 · Tobacco Products Control Regulations 2006 | STANDARDS: CODES OF PRACTICE: GUIDANCE'S: · Appendix to NOHSC guidance note on elimination of tobacco smoke · Guidance Note on Elimination of Environmental Tobacco Smoke in
3.6 | Alcohol and Other Drugs | · Injury / heath impacts · Affect on performance · Inappropriate behaviour · Discarded needles | OHS | 3 | 1 | 3 | · Responsible serving of alcohol requirements · Counselling services · Health promotion · Supervision · Security Services | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 | STANDARDS: CODES OF PRACTICE: GUIDANCE'S: · Alcohol and Other Drugs at the Workplace
4.1 | Clients, Customers and General Public | · Injury and/or property damage · Unfamiliar with Commission OSH procedures · Activities that adversely impact on the Commission environment and/or staff | OHS | 3 | 2 | 6 | · Maintenance and lighting · Direct and indirect supervision · Restricted access to Commission facilities and property · Supervision · 24 hour security support · Inductions · Public liability insurance | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 | STANDARDS: CODES OF PRACTICE: GUIDANCE'S:
4.2 | Contractors | · Unfamiliar with workplace and OSH procedures · High risk and/or specialised tasks · Work that adversely impacts on the Commission personnel and/or environment · Conducting unsafe work practices in conflict with Commission procedures | OHS | 3 | 2 | 6 | · Use of Preferred contractors (list) · Contractor agreed scope of works and/or contracts prior to commencing work · Contractor induction, SM Plan, JSA requirements · Supervision of works and contractors by Project Officers or Commission personnel · Contractor performance monitoring and reviews | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 · Refer to specific hazard classification for legislation | Refer to specific hazard classification for Standards/Codes/Guidance STANDARDS: · National Occupational Health and Safety Certification Standard for Users and Operators of industrial Equipment (NOHSC: 1006 2001) CODES OF PRACTICE: GUIDANCE'S: · Plant in the Workplace
4.3 | After Hours Work | · Working alone · Reduction in emergency assistance and support | OHS | 3 | 2 | 6 | · Risk assessments · Communication systems · Training/Induction · Restricted access to buildings and property · 24 hour security support and escort | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 | STANDARDS: CODES OF PRACTICE: · Code of Practice Working Hours GUIDANCE'S: · Working Alone Guidance Note · National Guidelines for Working Alone or in a Remote Locality [Commonwealth Safety Management Forum] (also cited under Travel and Off-location activities)
5.1 | Purchasing | · Introducing hazards into the workplace: - plant and equipment (including electrical) - chemicals and substances - radiation sources - office furniture and equipment - personal protective equipment · Introducing new and/or uncontrolled wastes | OHS | 3 | 1 | 3 | · Pre-purchase safety considerations: - plant and equipment (including electrical) - chemicals and substances - radiation sources - office furniture and equipment - personal protective equipment | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996: Part 3 - Workplace Safety Requirements, Part 4 - Plant | Refer to specific hazard classification for Standards/Codes/Guidance STANDARDS: CODES OF PRACTICE: GUIDANCE'S:
5.2 | Emergency Incident | · Uncontrolled emergency incident leading to adverse outcomes: - Loss of life - injury or illness - Property damage - Environmental impacts · Loss of communications · Loss of services · Breakdown in emergency procedures | OHS | 3 | 2 | 6 | · Commission emergency management plan · Inductions and training · Trained first aiders and building wardens · Scheduled building evacuations and exercises · Building essential services and ongoing maintenance of those services · Building specific emergency procedures and plans · Task/activity specific emergency procedures and plans (when required) | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 · Building Code of Australia | STANDARDS: · AS 3745 Emergency Control Organisation and Procedures for Buildings, Structures and Workplaces · AS 1603 (series) Automatic Fire Detection And Alarm Systems · AS 1670 (series) Fire Detection, · AS/NZS 1841 (series) Portable Fire Extinguishers CODES OF PRACTICE: GUIDANCE'S: · Preparing for emergency evacuations at the workplace Warning, Control And Intercom Systems
5.3 | Legal Compliance | · Injury and/or property damage · Prosecution and fines · Intervention programs · Reputation damage to the Commission | OHS | 3 | 2 | 6 | · Occupational Health and Safety Management System · Risk assessments · Licenses, Permits and Agreements · Authorising Officers · Records management and data control · OSHPAG · Safety and Health Representatives and designated work groups · Internal auditing · External auditing · Incident reporting, recording and management | 3 | 1 | 3 | Ongoing | 1. OSHPAG Meeting 2. Workplace Inspection Schedule 3. External auditor to conduct systems audit ever 6 months 4. Quarterly KPI reports to CEC | As per safety management plan and schedule | · Occupational Safety and Health Act 1984 · Occupational Safety and Health Regulations 1996 · Workers' Compensation and injury Management Act 1981 [WA] · Refer to category classification for specific legislation | STANDARDS: · AS/NZS 4804 Occupational health and safety management systems - General guidelines on principles, systems and supporting techniques · AS/NZS 4801: Occupational health and safety management systems - Specification with guidance for use · WorkSafe Plan · AS/NZS ISO 31000:2009 Risk Management – Principles and Guidelines CODES OF PRACTICE: GUIDANCE'S:

## Risk Scores
Consequences
|  |  | 1 | 2 | 3 | 4 | 5
Likelihood | 5 | Almost certain to occur in most circumstances | 5 | 10 | 15 | 20 | 25
| 4 | Likely to occur frequently | 4 | 8 | 12 | 16 | 20
| 3 | Possible and likely to occur at some time | 3 | 6 | 9 | 12 | 15
| 2 | Unlikely to occur but could happen | 2 | 4 | 6 | 8 | 10
| 1 | May occur but only in rare circumstances | 1 | 2 | 3 | 4 | 5

## Risk Matrix
MATRIX CHARTS
1
1
0
Likihood
Consequence
HIGH (4-5)
MEDIUM (3)
LOW (1-2)
HIGH(4-5)
MEDIUM (3)
LOW (1-2)
4
7
1
9
4
23

## Tables for Report
Extreme Risk
Risk | Risk Area | Consequence | Possible Control/Treatment Options | Likelihood | Risk Rating | Person Responsible | By when? | How will it be monitored | Further Action
[5 empty] | 0 | AW
[5 empty] | 12 | AK, KH
Medium / High Risk
Risk | Risk Area | Consequence | Possible Control/Treatment Options | Likelihood | Risk Rating | Person Responsible | By when? | How will it be monitored | Further Action
10
10
10
10
10
10
10
0
0
0
0
0
0
0
0
8
8

## RR (hidden)
Team | Risk Statement | Risk Area | Consequence | Likelihood | Inherent Risk Rating | Possible Control/Treatment Options | Likelihood with control | Residual risk rating | Person Responsible | By when? | How will it be monitored | Further Action | Legislation | Standards/ Codes/ guidance
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS
OHS